## Sheet1
Balmala
2025-03-11
Stem Ripper: Complete
demuextract
Tempo Detection: Complete
Liborosa
Note Detection: Incomplete | Needs: | Liborosa detect when a note is played at the frequency of a kick.
Liborosa |  | First sample 8 bars and make sure notes do not jumble
ISSUE, the ppq may not be stored properly, jumbling notes, but does detect at the correct time, just does not create the midi file correct
Correct PPQ for future
*IDEA: FIRST ##UDATE JUICE## Double the length of the ticks and time so that it matches up, then double that and it might solve problem
Solution: Made sure correct files were adjusted, they are now showing 960 ppq, issue is rounding up, now need to round to nearest whole number
NOW: Note placements are off by :13, considered librosa picking the wrong peak, but that’s unlikely, need to figure out offset or what its picking up
Do research on phenomenom to figure out if its regular and other people solution
Figure out how to match the detection of tempo with the correct note placement
If succesful, configure range to detect snares
If succesful, configure range to detect hats
If succesful, add to current version of Balama, It will then be V2
Time Scrubber: NO START | Needs: | To be able to detect the sample I want convered to midi, I will need to add a scrubber, increasing time if stable
Liborosa |  | Be able to select file and playback within gui
C++ |  | Have the scrubber change the where the start point of the sample will begin and will automatically end
visual audio waves for gui
Be able to select which stem to extract to midi, (will be able to automate the process of running demuextract and select the drum file if the drum file wasn’t already selected.
Note detection for mids: NO START | Needs: | To be able to detect mid notes and overvall melodic pattern in selected sample
Liborosa
…
Beat randomizer: NO START | Needs: | BASIC FRAME (can place kicks in a pattern, as well as hats and snares)
Liborosa |  | Select a chord progression and liborosa will make the midi
Random melody from song key
…
FUTURE PLANS
AI Integration
Beat type Detection
Beat generate based on type
Can generate similar song to one selected